## Worksheet
Logistics Planning - Financial View
Project Phase | Description | Planned Start Date | Planned End Date | Budget (USD) | Actual Spend (USD) | Status
Planning & Design | Route planning, supplier selection, warehouse setup. | 2024-01-15 | 2024-03-15 | $75,000 | $68,500 | In Progress
Procurement & Sourcing | Ordering materials and securing transportation. | 2024-03-16 | 2024-05-31 | $185,000 | $179,350 | In Progress
Transportation & Distribution | Shipping goods across regional hubs. | 2024-06-01 | 2024-08-31 | $315,000 | $317,895 | On Hold (Delays)
Inventory Management Setup | Implementing tracking systems and storage protocols. | 2024-07-15 | 2024-09-30 | $65,000 | $63,150 | On Track
Final Review & Reporting | Evaluation of KPIs and financial performance. | 2024-10-01 | 2024-10-31 | $35,000 | $5,789 | Pending Start