## Worksheet
Logistics Planning - Project Template
Phase | Activity | Responsible Party | Start Date | End Date | Status
Planning | Define project scope and objectives | Project Manager | 2024-04-01 | 2024-04-05 | In Progress
Sub-tasks for Phase 1:
| Identify key logistics requirements | Logistics Coordinator | 2024-04-06 | 2024-04-10 | Pending
Phase | Activity | Responsible Party | Start Date | End Date | Status
Procurement | Select transportation partners and vendors | Procurement Lead | 2024-04-11 | 2024-04-18 | Pending
Sub-tasks for Phase 2:
| Negotiate contracts and service agreements | Legal & Contracts Team | 2024-04-19 | 2024-04-25 | Pending
Phase | Activity | Responsible Party | Start Date | End Date | Status
Execution | Dispatch initial shipments and track deliveries | Logistics Supervisor | 2024-04-26 | 2024-05-10 | Pending
Sub-tasks for Phase 3:
| Monitor inventory levels and supply chain performance | Supply Chain Analyst | 2024-05-11 | 2024-05-17 | Pending
| Cycle time optimization and bottlenecks analysis | Ongoing Review Process |  |  | In Progress
Phase | Activity | Responsible Party | Start Date | End Date | Status
Monitoring & Evaluation | Conduct weekly logistics performance reviews | Project Manager | 2024-05-18 | Ongoing (Monthly)
Sub-tasks for Phase 4:
| Update project dashboard and share with stakeholders | Reporting Officer | 2024-05-20 | Ongoing (Bi-weekly)
Phase | Activity | Responsible Party | Start Date | End Date | Status
Closure | Finalize all logistics documentation and contracts | Project Manager & Legal Team | 2024-06-01 | TBD
Sub-tasks for Phase 5:
Celebrate project completion and share lessons learned | All Team Members | 2024-06-15 | TBD
© 2024 Logistics Planning Project Template ¦ Multi-Page Version ¦ For internal use only