## Worksheet
Logistics Planning - Project Template
One Page ¦ Purpose: Logistics Planning ¦ Template Type: Project Template
Project Phase | Key Activity | Timeline (Weeks) |  |  | Responsible Team | Status
|  | Start | End | Durations
Planning & Requirements | Gather logistics requirements and constraints | 1 | 2 | 2 weeks | Logistics Team | In Progress
Procurement & Sourcing | Identify suppliers and vendors | 3 | 4 | 2 weeks | Sourcing Team | Pending Review
| Negotiate contracts and pricing terms | 5 | 6 | 2 weeks | Sourcing & Legal Team | Pending Approval
| Confirm supplier commitments | 7 | 8 | 2 weeks | Sourcing Team | Pending Sign-Off
Transportation & Routing | Map out transport routes and schedules | 9 | 10 | 2 weeks | Fleet & Ops Team | Pending Review
| Select carriers and freight modes | 11 | 12 | 2 weeks | Fleet & Ops Team | Pending Approval
| Finalize delivery timelines and KPIs | 13 | 14 | 2 weeks | Fleet & Ops Team | Pending Finalization
Inventory & Warehouse Management | Assign warehouse locations and storage plans | 15 | 16 | 2 weeks | Warehouse Team | In Progress
| Create inventory forecast and safety stock levels | 17 | 18 | 2 weeks | Supply Chain Analysts | Pending Review
| Implement tracking system and WMS setup | 19 | 20 | 2 weeks | IT & Warehouse Team | Pending Initiation
Execution & Monitoring | Launch pilot logistics run (test phase) | 21 | 22 | 2 weeks | All Teams | Pending Launch
| Monitor performance and adjust operations in real-time | 23 | 26 | 4 weeks | Fleet & Ops Team | Pending Start
| Capture feedback and optimize delivery process | 27 | 28 | 2 weeks | Project Manager & Logistics Team | Pending Start
Closure & Review | Finalize documentation and handover | 29 | 30 | 2 weeks | Project Manager | Pending Start
| Closure meeting and lessons learned session | 31 | 32 | 2 weeks | All Stakeholders | Pending Start
Total Duration: |  | 32 weeks
Note:This template is designed for a one-page logistics planning project. Update status regularly and use color coding to reflect progress (e.g., green = completed, yellow = in progress, red = delayed).