## Worksheet
Logistics Planning - Project Template (Planning View)
Task ID | Task Name | Assigned To | Start Date | End Date | Status | % Complete | Budget (USD) | Priority | Notes/Dependencies
LPT-001 | Route Analysis & Selection | Logistics Team A | 2024-04-01 | 2024-04-15 | In Progress | 65% | $15,000 | High | Requires weather data from regional office.
LPT-002 | Warehouse Capacity Assessment | Operations Analysts | 2024-04-16 | 2024-04-30 | Pending | 0% | $8,500 | Medium | Awaiting facility access permission.
LPT-003 | Vessel Booking & Scheduling | Shipping Coordinator | 2024-05-01 | 2024-05-14 | Not Started | 0% | $35,750 | High | Must align with port availability.
LPT-004 | Inventory Allocation Planning | Supply Chain Manager | 2024-05-15 | 2024-05-31 | Not Started | 0% | $12,300 | High | Dependent on vessel arrival.
Resource Allocation Summary
Total Tasks | 4 | Total Budget (USD) | $71,550 | Average Progress | 16% | High Priority Tasks | 3
This template is designed for logistics planning in project management. Update statuses, dates, and allocations as the project progresses.