## Worksheet
Logistics Planning - Project Template
Template Type:Project Template ¦Purpose:Logistics Planning ¦Style/Version:Printable
Task ID | Task Description | Schedule |  |  | Resource Allocation |  | Status
|  | Start Date | End Date | Duration (Days) | Assigned To | Role/Responsibility
P001 | Project Kickoff & Planning | 2024-04-01 | 2024-04-05 | 5 | Jane Doe | Project Manager | In Progress
P002 | Route Mapping & Optimization | 2024-04-06 | 2024-04-15 | 10 | John Smith | Traffic Analyst | In Progress
P003 | Vendor & Supplier Coordination | 2024-04-16 | 2024-04-25 | 10 | Alice Brown | Sourcing Coordinator | Pending Approval
P004 | Warehouse Setup & Inventory Prep | 2024-04-18 | 2024-05-10 | 23 | Robert Lee | Operations Lead | Pending Approval
P005 | Transportation Booking & Carrier Selection | 2024-04-26 | 2024-05-15 | 21 | Susan Clark | Fleet Coordinator | Pending Approval th>
P006 | Tracking System Integration (WMS/ERP) | 2024-05-11 | 2024-05-31 | 21 | Mark Wilson | Tech Integrator | Pending Approval th>
P007 | Final Testing & Dry Run Simulation | 2024-06-01 | 2024-06-15 | 15 | All Teams | Cross-functional Team | Pending Approval th>
P008 | Project Closure & Reporting | 2024-06-16 | 2024-06-30 | 15 | Jane Doe | Project Manager | Pending Approval th>
Total Tasks: |  | 8
Printed on:¦ Template Version: 1.0 ¦ Confidential - For Internal Use Only