## Worksheet
Logistics Planning - Project Template
Task ID | Task Name | Description | Responsible Party | Status | Start Date | End Date
LPT-001 | Transportation Route Planning | Develop and validate optimal transportation routes for delivery schedules. | Logistics Manager | In Progress | 2024-04-05 | 2024-04-15
LPT-002 | Warehouse Inventory Audit | Conduct a full inventory check at regional distribution centers. | Inventory Supervisor | Planned | 2024-04-16 | 2024-04-18
LPT-003 | Carrier Contract Review | Evaluate current carrier contracts and negotiate improved terms. | Procurement Lead | On Hold | 2024-04-19 | 2024-05-15
LPT-004 | Distribution Center Capacity Assessment | Analyze capacity and scalability of existing distribution centers. | Operations Analyst | Completed | 2024-03-15 | 2024-03-31
LPT-005 | Sustainability Initiative Implementation | Introduce eco-friendly packaging and carbon-neutral shipping options. | Sustainability Coordinator | Planned | 2024-05-16 | 2024-06-30
Total Tasks: |  |  |  |  | 5