## Worksheet
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | Priority
T001 | Initial Planning Meeting | Project Manager | 2024-04-05 | 2024-04-05 | To Do | High
T002 | Route Optimization Analysis | Logistics Analyst | 2024-04-06 | 2024-04-12 | In Progress | High
T003 | Carrier Selection and Contracts | Procurement Team | 2024-04-13 | 2024-04-19 | To Do | High
T004 | Inventory Pre-positioning | Warehouse Manager | 2024-04-20 | 2024-04-25 | To Do | Moderate
T005 | Transportation Scheduling | Logistics Coordinator | 2024-04-26 | 2024-05-03 | To Do | High
T006 | Real-time Tracking Setup | IT Department | 2024-05-04 | 2024-05-10 | To Do | Moderate
T007 | Final Review and Approval | Project Manager | 2024-05-11 | 2024-05-13 | To Do | High
Project Summary:
Total Tasks:7
In Progress:1
To Do:5
Completed:1
Generated on: