## Worksheet
LOGISTICS PLANNING - PROJECT TEMPLATE (STARTUP)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | Budget (USD) | Milestone Achieved?
#LP001 | Initial Site Assessment & Route Planning | Operations Team | 2024-04-05 | 2024-04-12 | Pending | $5,800 | No
#LP002 | Vendor & Carrier Selection (Local) | Procurement Team | 2024-04-13 | 2024-04-19 | In Progress | $8,500 | No
#LP003 | Inventory & Warehouse Setup (Phase 1) | Supply Chain Team | 2024-04-20 | 2024-05-15 | In Progress | $35,750 | No
#LP004 | Transportation Route Optimization (Software Integration) | Tech & Analytics Team | 2024-05-16 | 2024-05-31 | Pending | $12,900 | No
#LP005 | First Shipment Trial Run (Internal) | Operations Team | 2024-06-01 | 2024-06-15 | Pending | $9,850 | No
#LP006 | Performance Review & Feedback Loop Implementation | Project Management Office (PMO) | 2024-06-16 | 2024-07-31 | Pending | $7,500 | No