## Worksheet
Logistics Planning - Tracking View
Project ID | Task Name | Assigned To | Start Date | End Date | Status | Progress (%)
PJ-LG-001 | Route Planning & Approval | Sarah Johnson | 2023-10-05 | 2023-10-12 | Pending | 45%
PJ-LG-002 | Supplier Coordination | Michael Chen | 2023-10-07 | 2023-10-18 | Pending | 65%
PJ-LG-003 | Inventory Check & Allocation | Lisa Ramirez | 2023-10-10 | 2023-10-25 | Completed | 100%
PJ-LG-004 | Transportation Booking | Daniel Park | 2023-10-15 | 2023-11-05 | Pending | 30%
PJ-LG-005 | Delivery Schedule Finalization | Amina Diallo | 2023-11-01 | 2023-11-15 | Delayed | 75%