## Worksheet
Task | Start Date | End Date | Responsible Party | Status
Initial Planning Meeting | 2024-01-05 | 2024-01-07 | Project Manager | In Progress
Sourcing Suppliers | 2024-01-08 | 2024-01-15 | Procurement Team | Pending
Transportation Route Planning | 2024-01-16 | 2024-01-23 | Logistics Coordinator | Pending
Warehousing Setup | 2024-01-24 | 2024-01-31 | Fulfillment Team | Pending
Inventory Import & Verification | 2024-02-01 | 2024-02-07 | Inventory Manager | Pending
Loading & Dispatch Preparation | 2024-02-08 | 2024-02-15 | Logistics Team | Pending
Final Delivery & Handover | 2024-02-16 | 2024-02-23 | Distribution Manager | Pending