## Worksheet
Logistics Planning - Project Timeline
Task ID | Activity Description | Responsible Team | Start Date | End Date | Status
T001 | Initial Planning & Requirement Gathering | Logistics Team | 2024-04-01 | 2024-04-05 | Completed
T002 | Route Optimization Analysis | Operations & Analytics | 2024-04-06 | 2024-04-15 | In Progress
T003 | Vendor Contract Finalization | Purchasing & Legal | 2024-04-16 | 2024-04-25 | Pending
T004 | Warehouse Preparation & Inventory Setup | Supply Chain & Warehouse | 2024-04-26 | 2024-05-10 | Pending
T005 | Transportation Booking & Dispatch Schedule | Logistics Coordination | 2024-05-11 | 2024-05-31 | Pending
T006 | Real-Time Tracking System Integration | IT & Logistics Tech | 2024-05-15 | 2024-05-31 | Pending
T007 | Final Audit & Risk Assessment Review | Quality Assurance & Compliance | 2024-06-01 | 2024-06-15 | Pending
T008 | Project Closure & Handover Report | Project Management Office | 2024-06-16 | 2024-06-30 | Pending