## Worksheet
Logistics Planning - Project Timeline (Client View)
Phase | Task | Start Date | End Date | Status | Owner | Budget (USD)
Planning & Coordination | Requirement Gathering & Analysis | 2024-05-01 | 2024-05-10 | Completed | Jane Doe (Logistics Lead) | $8,500
| Route Optimization & Risk Assessment | 2024-05-11 | 2024-05-17 | Completed | Mike Chen (Ops Analyst) | $6,200
| Vendor Contract Finalization | 2024-05-18 | 2024-05-31 | In Progress | Sarah Kim (Procurement) | $18,300
Execution Phase | Warehouse Preparation & Inventory Setup | 2024-06-01 | 2024-06-15 | In Progress | Liam Turner (Warehouse Manager) | $15,750
| Transportation Dispatch & Tracking Setup | 2024-06-16 | 2024-06-30 | In Progress | Elena Rodriguez (Carrier Coordinator) | $12,950
| First Shipment Delivery (Prototype Batch) | 2024-07-01 | 2024-07-15 | Delayed | Martin Lee (Delivery Supervisor) | $9,600
| Performance Monitoring & KPI Reporting | 2024-07-16 | 2024-07-31 | Delayed | Sophie Adams (Data Analyst) | $5,800
Finalization & Review | Client Feedback Collection & Integration | 2024-08-01 | 2024-08-15 | Delayed | Jane Doe (Logistics Lead) | $3,950
| Project Handover & Documentation Finalization | 2024-08-16 | 2024-08-31 | Delayed | Mike Chen (Ops Analyst) | $7,150
Total Estimated Budget: | [5 empty] | $98,200