## Worksheet
Date | Task Description | Responsible Team/Person | Status
2023-10-01 | Initial Logistics Assessment & Site Survey | Logistics Team Lead, Operations Manager | In Progress
2023-10-02 | Confirm Transportation Routes and Permits | Fleet Coordinator, Legal Compliance | To Do
2023-10-03 | Finalize Inventory Allocation Plan | Supply Chain Analyst, Warehouse Manager | In Progress
2023-10-04 | Dispatch Preparations: Packaging & Labeling Review | Packaging Supervisor, QA Inspector | To Do
2023-10-05 | Driver Briefings & Route Simulation Testing | Logistics Coordinator, Dispatch Manager | To Do
2023-10-06 | First Shipment Trial Run (Internal) | Fleet Driver, Logistics Team Lead | To Do
2023-10-07 | Evaluate Trial Run Performance & Adjust Plan | Project Manager, Operations Team | To Do
Notes:This daily project timeline is intended for logistics planning purposes. Update status daily and adjust resources as needed to ensure on-time delivery and efficient operations.