## Worksheet
Logistics Planning - Project Timeline Dashboard
Task ID | Activity Description | Assigned To | Start Date | End Date | Status | % Complete
T001 | Route Planning & Optimization | Logistics Team A | 2024-04-01 | 2024-04-15 | In Progress | 65%
T002 | Warehouse Inventory Check | Inventory Control | 2024-04-03 | 2024-04-18 | In Progress | 55%
T003 | Carrier Contract Finalization | Procurement Team | 2024-04-10 | 2024-04-25 | Pending | 15%
T004 | Transport Schedule Coordination | Logistics Team B | 2024-04-15 | 2024-05-10 | Pending | 8%
T005 | Delivery Tracking System Setup | IT Support | 2024-04-20 | 2024-05-15 | Pending | 3%
T006 | Final Logistics Audit & Review | Audit Team | 2024-05-11 | 2024-05-18 | Pending | 0%