## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Resource Assigned | Status
T001 | Project Initiation | 2023-10-01 | 2023-10-05 | 5 | Project Manager | In Progress
T002 | Route Planning & Approval | 2023-10-06 | 2023-10-15 | 10 | Logistics Coordinator | In Progress
T003 | Fleet Preparation & Maintenance | 2023-10-16 | 2023-10-25 | 10 | Fleet Manager | To Do
T004 | Warehouse Loading & Packaging | 2023-10-26 | 2023-11-05 | 10 | Warehouse Team Lead | To Do
T005 | Transportation Execution (Phase 1) | 2023-11-06 | 2023-11-15 | 10 | Fleet Driver Team | To Do
T006 | Delivery & Unloading at Hub 1 | 2023-11-16 | 2023-11-20 | 5 | Field Supervisor | To Do
T007 | Transportation Execution (Phase 2) | 2023-11-21 | 2023-11-30 | 10 | Fleet Driver Team | To Do
T008 | Final Delivery & Customer Handover | 2023-12-01 | 2023-12-10 | 10 | Customer Service Team | To Do
T009 | Post-Project Review & Reporting | 2023-12-11 | 2023-12-15 | 5 | Project Manager | To Do