## Worksheet
Logistics Planning - Project Timeline (Detailed)
Task ID | Task Name | Description | Start Date | End Date | Duration (Days) | Status | Responsible Team/Person
T001 | Project Initiation & Planning | Define project scope, objectives, and deliverables. Identify stakeholders. | 2023-10-01 | 2023-10-05 | 5 | In Progress | Project Manager, Logistics Team
T002 | Route & Transport Strategy Development | Map optimal delivery routes, assess carrier options, and evaluate transportation modes. | 2023-10-06 | 2023-10-15 | 10 | In Progress
T003 | Warehouse Facility Assessment | Evaluate current storage capacity, infrastructure, and location efficiency. | 2023-10-16 | 2023-10-25 | 10 | Pending
T004 | Inventory Forecasting & Stock Planning | Analyze demand patterns and determine optimal stock levels for key regions. | 2023-10-26 | 2023-11-05 | 10 | Pending
M001 | Phase 1 Complete: Planning & Assessment Approved | All planning documents reviewed and approved by stakeholders. | 2023-11-06 | 2023-11-07 | 2 | Not Started
T005 | Supplier & Vendor Contract Finalization | Negotiate and sign contracts with key suppliers and logistics partners. | 2023-11-08 | 2023-11-20 | 13 | Pending
T006 | Technology Integration (TMS & WMS) | Implement and test Transportation Management System (TMS) and Warehouse Management System (WMS). | 2023-11-21 | 2023-12-05 | 15 | Pending
T007 | Staff Training & Onboarding | Train logistics team on new systems, processes, and safety protocols. | 2023-12-06 | 2023-12-15 | 10 | Pending
M002 | Phase 2 Complete: System & Team Readiness Achieved | All systems integrated; team trained and certified for operations. | 2023-12-16 | 2023-12-17 | 2 | Not Started
T008 | Pilot Launch: Regional Logistics Run | Execute controlled pilot program for one distribution hub. | 2023-12-18 | 2024-01-15 | 28 | Pending
T009 | Performance Monitoring & Feedback Collection | Gather operational data, identify bottlenecks, and collect team feedback. | 2024-01-16 | 2024-01-31 | 16 | Pending
T010 | Full-Scale Rollout & Optimization | Scale logistics operations across all regions with continuous improvement. | 2024-02-01 | 2024-12-31 | 335 | Pending
M003 | Project Completion: Full Operations Live | All logistics processes operational with defined KPIs and reporting. | 2024-12-31 | 2024-12-31 | 0 | Not Started
Note:This timeline is based on current estimates and may be revised during project execution. Status updates are scheduled bi-weekly.