## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Responsible Party(Department/Team)(Contact Info) | Dependencies(Previous Tasks) | Milestones Achieved(Key Checkpoints) | Budget Allocation (USD)
001 | Project Initiation & Planning | 2024-10-05 | 2024-10-15 | 11 | Completed | Sarah Johnson Logistics Planning Team sarah.johnson@logisticsco.com | N/A | Project Charter Approved, Stakeholders Aligned, Timeline Finalized | $12,500
002 | Route & Carrier Selection | 2024-10-16 | 2024-11-15 | 30 | In Progress | Marcus Lee Transportation Division marcus.lee@logisticsco.com | Task 001 | Candidate Routes Mapped, Carrier Shortlist Finalized | $38,750
003 | Warehouse Facility Assessment | 2024-10-18 | 2024-11-30 | 43 | In Progress | Lisa Chen Fleet & Warehousing lisa.chen@logisticsco.com | Task 001, Task 002 | Facility Survey Completed, Storage Capacity Verified | $24,300
004 | Inventory Planning & Procurement Scheduling | 2024-11-16 | 2025-01-31 | 77 | To Do | James Park Purchasing & Inventory james.park@logisticsco.com | Task 002, Task 003 | Master Inventory List Finalized, Initial Order Placed | $145,800
005 | Transportation & Logistics Coordination (Phase 1) | 2025-02-01 | 2025-03-31 | 60 | To Do | Nina Patel Operations Coordination nina.patel@logisticsco.com | Task 004, Task 012 (if applicable) | First Shipment Dispatched, Real-Time Tracking System Deployed | $98,250
006 | Safety & Compliance Audits (Pre-Deployment) | 2025-01-15 | 2025-03-31 | 76 | To Do | Alex Turner Compliance & QA alex.turner@logisticsco.com | Task 003, Task 004 | Audit Checklist Completed, Regulatory Approvals Secured | $18,650
007 | Technology Integration (Tracking & Reporting) | 2024-11-30 | 2025-04-30 | 183 | To Do | Daniel Wu IT Systems Integration daniel.wu@logisticsco.com | Task 002, Task 016 (if applicable) | System Interface Developed, Test Version Live | $75,400
008 | Team Training & Onboarding (Logistics Staff) | 2025-03-15 | 2025-04-30 | 46 | To Do | Rachel Simmons Talent Development rachel.simmons@logisticsco.com | Task 005, Task 017 (if applicable) | Training Modules Completed, Certification Passed | $22,900
009 | First Pilot Shipment & Feedback Loop | 2025-05-15 | 2025-06-30 | 46 | To Do | Ethan Reed Pilot Program Lead ethan.reed@logisticsco.com | Task 005, Task 006, Task 018 (if applicable) | Pilot Shipment Delivered Successfully, Feedback Collected & Analyzed | $43,250
010 | Full-Scale Operations Launch (Phase 1) | 2025-07-01 | 2025-12-31 | 184 | To Do | Sophia Bennett Operations Director sophia.bennett@logisticsco.com | Task 009, Task 013, Task 014 | Operations Fully Operational, KPIs Monitored Weekly | $525,750
Total Budget: | $1,024,600