## Worksheet
Logistics Planning - Project Timeline (Financial View)
Task ID | Task Description | Start Date | End Date | Budget (USD) | Status
TASK-001 | Route Planning & Optimization | 2024-04-01 | 2024-04-15 | $8,500 | Completed
TASK-002 | Carrier Selection & Contracting | 2024-04-16 | 2024-05-10 | $15,300 | Completed
TASK-003 | Inventory Allocation & Warehouse Prep | 2024-05-11 | 2024-06-15 | $23,750 | Completed
TASK-004 | Transportation Schedule Finalization | 2024-06-16 | 2024-07-31 | $35,800 | Delayed
TASK-005 | Real-Time Tracking System Deployment | 2024-08-01 | 2024-09-15 | $18,650 | Pending
TASK-006 | Final Logistics Review & Audit | 2024-09-16 | 2024-10-31 | $12,450 | Pending
Total Project Budget |  |  |  | $114,450