## Worksheet
Freelancer Project Timeline - Logistics Planning
Task ID | Task Description | Start Date | End Date | Status | Assigned To | Action
#LGT-001 | Initial Logistics Assessment & Site Survey | 2024-04-05 | 2024-04-12 | In Progress | Jane Doe (Logistics Lead) | Update
#LGT-002 | Develop Route Optimization Plan | 2024-04-13 | 2024-04-19 | Pending | Mark Taylor (Route Analyst) | Update
#LGT-003 | Vendor & Carrier Selection & Contracting | 2024-04-20 | 2024-04-30 | Pending | Sarah Kim (Procurement) | Update
#LGT-004 | Warehouse Preparation & Inventory Setup | 2024-05-01 | 2024-05-15 | Pending | Alex Rivera (Ops Coordinator) | Update
#LGT-005 | First Delivery Test Run & Feedback Collection | 2024-05-16 | 2024-05-23 | Pending | Jane Doe (Logistics Lead) | Update
#LGT-006 | Full-Scale Logistics Deployment | 2024-05-24 | 2024-06-15 | Pending | All Team Members | Update
#LGT-007 | Performance Review & Final Report Submission | 2024-06-16 | 2024-06-30 | Pending | Sarah Kim (Procurement) | Update