## Worksheet
Logistics Planning - Project Timeline (Home Use)
Task ID | Task Description | Start Date | End Date | Status | Responsible Person
T001 | Route Planning & Optimization | 2024-04-05 | 2024-04-15 | Pending | Jane Smith
T002 | Carrier Selection & Contracting | 2024-04-16 | 2024-04-30 | Pending | Mike Johnson
T003 | Inventory Preparation & Packaging | 2024-05-01 | 2024-05-15 | Pending | Sarah Lee
T004 | Transportation Scheduling & Dispatching | 2024-05-16 | 2024-05-31 | Pending | David Brown
T005 | Real-Time Tracking Setup & Integration | 2024-06-01 | 2024-06-15 | Pending | Alex Chen
T006 | Delivery & Last-Mile Coordination | 2024-06-16 | 2024-07-15 | Pending | Lisa White
T007 | Post-Delivery Reporting & Feedback Collection | 2024-07-16 | 2024-08-15 | Pending | Ryan Clark
Project Duration:April 5, 2024 – August 15, 2024
Status Update Date:April 1, 2024