## Worksheet
Logistics Planning - Project Timeline
Large Business Template • Version 2.0 • Q3 2024
Phase | Task | Start Date | End Date | Status | Budget (USD)
Planning & Procurement | Vendor Contract Finalization | 2024-07-01 | 2024-07-15 | Completed | $85,000
| Raw Material Procurement | 2024-07-16 | 2024-08-15 | In Progress | $345,000
| Logistics Equipment Procurement | 2024-07-20 | 2024-08-10 | In Progress | $189,500
Transportation & Distribution | Route Optimization & Permitting | 2024-08-16 | 2024-08-31 | In Progress | $57,300
| Primary Shipment Execution (Region A) | 2024-09-01 | 2024-10-15 | In Progress | $678,900
| Secondary Shipment Execution (Region B) | 2024-10-16 | 2024-11-30 | Delayed | $598,400
Warehousing & Inventory Control | Warehouse Setup (Regional Hub 1) | 2024-09-15 | 2024-10-31 | In Progress | $234,600
| Inventory System Integration | 2024-11-01 | 2024-11-30 | Delayed | $89,750
Monitoring & Reporting | Real-Time Tracking Deployment | 2024-10-15 | 2024-11-30 | In Progress | $98,500
| Final Audit & Project Review | 2024-12-01 | 2024-12-15 | Delayed | $65,800
TOTAL BUDGET: |  |  |  |  | $2,277,750