## Worksheet
Logistics Planning - Project Timeline - Manager View
Phase / Task | Start Date | End Date | Status | Owner | Budget (USD)
Planning & Preparation Phase
Route Assessment & Risk Analysis | 2023-10-01 | 2023-10-15 | In Progress | Jane Cooper | $8,500
Supplier Contract Finalization | 2023-10-10 | 2023-10-25 | Pending | Liam Reed | $45,000
Procurement & Warehousing Phase
Inventory Procurement Order Placement | 2023-11-01 | 2023-11-15 | Pending | Mia Patel | $67,800
Warehouse Space Allocation & Setup | 2023-11-05 | 2023-11-20 | Pending | Noah Wright | $15,400
Transportation & Distribution Phase
Carrier Selection & Booking Confirmation | 2023-11-25 | 2023-12-05 | Pending | Sophia Hall | $98,700
Final Dispatch & Shipment Tracking Setup | 2023-12-06 | 2023-12-15 | Pending | Ava Martin | $7,950
Monitoring & Closure Phase
Real-Time Shipment Monitoring & Reporting | 2023-12-16 | 2024-01-31 | Pending | Ethan Young | $36,500
Performance Review & Project Closure | 2024-02-01 | 2024-02-15 | Pending | Jane Cooper | $9,800