## Worksheet
Logistics Planning - Project Timeline
Multi-Page Template ¦ Prepared for Logistics Coordination Team
Phase | Task Name | Start Date | End Date | Responsible Team | Status
1. Planning | Preliminary Logistics Assessment | 2024-04-01 | 2024-04-15 | Logistics Team A | In Progress
Preparation of Route Maps & Risk Analysis (Sub-tasks)
| Risk Assessment & Contingency Planning | 2024-04-16 | 2024-04-30 | Logistics Team B | Pending
2. Procurement | Supplier Selection & Contracting | 2024-05-01 | 2024-05-15 | Purchasing Dept. | In Progress
Procurement of Transport & Storage Equipment (Sub-tasks)
| Equipment Delivery Schedule Confirmation | 2024-05-16 | 2024-05-31 | Logistics Team C | Pending
3. Transportation | Vehicle Dispatch Planning & Route Optimization | 2024-06-01 | 2024-06-15 | Fleet Management | Pending (Next)
Load Preparation & Cargo Securing (Sub-tasks)
| Cargo Loading & Documentation Finalization | 2024-06-16 | 2024-06-30 | Loading Team 1 | Pending (Next)
Transport Execution & Monitoring (Sub-tasks)
4. Delivery & Tracking | Real-Time Shipment Tracking Setup | 2024-07-01 | 2024-07-15 | IT & Logistics Coordination
Delivery Execution & On-Site Receipt Confirmation (Sub-tasks)
| Final Delivery & Client Handover | 2024-07-16 | 2024-07-31 | Field Operations Team
5. Review & Closeout | Post-Delivery Performance Review Meeting | 2024-08-01 | 2024-08-15 | Project Management Office (PMO)
Documentation Archiving & Lessons Learned Report
Generated on: 2024-04-05 ¦ Page 1 of 3 ¦ Confidential - For Internal Use Only
Logistics Planning - Project Timeline (Continued)
Multi-Page Template ¦ Prepared for Logistics Coordination Team
Key Milestones | Target Date | Status | Remarks / Dependencies
Final Route Approval from Regulatory Bodies | 2024-04-18 | In Progress | Awaiting customs clearance approval
All Procurement Contracts Signed | 2024-05-15 | Pending (Next) | Supplier negotiations ongoing
Vehicles & Equipment Received on Site | 2024-06-15 | Pending (Next) | Delivery confirmation pending from vendor A
First Shipment Dispatched to Regional Hub | 2024-07-15
Complete Delivery to All Destinations Achieved | 2024-07-31
Final Project Review Report Submitted | 2024-08-15
Page 2 of 3 ¦ Generated on: 2024-04-05 ¦ Confidential - For Internal Use Only
Logistics Planning - Project Timeline (Final Page)
Multi-Page Template ¦ Prepared for Logistics Coordination Team
Resource Allocation Summary | Quantity/Units | Assigned To | Status
Trucks (Flatbed) | 12 units | Fleet Management Team | Allocated - 9 active, 3 on standby
Dedicated Drivers (Full-time) | 24 personnel - Scheduled shifts in rotation
Refrigerated Vans (Cold Chain) | 6 units | Pending final inspection
Warehouse Storage Capacity Used (m²) | 1,800 m² | Within allocated limit
Safety & Compliance Certifications (All Vehicles) | Pending final audit report - Due 2024-05-31
Page 3 of 3 ¦ Generated on: 2024-04-05 ¦ Confidential - For Internal Use Only
End of Document
This project timeline template is designed for multi-page Excel-like presentation. Print or export as PDF for distribution.