## Worksheet
Logistics Planning - Project Timeline (Office Use)
Phase | Task | Start Date | End Date | Responsible Team | Status
Planning | Requirement Analysis & Scope Definition | 2024-04-01 | 2024-04-15 | Project Management | In Progress
Procurement | Sourcing of Materials and Suppliers Selection | 2024-04-16 | 2024-05-10 | Purchasing Team | Not Started
Transportation | Logistics Route Optimization & Carrier Booking | 2024-05-11 | 2024-05-31 | Transportation Coordination | Not Started
Warehousing | Inventory Planning & Warehouse Preparation | 2024-06-01 | 2024-06-15 | Supply Chain Operations | Not Started
Distribution | Final Delivery Scheduling & Tracking Setup | 2024-06-16 | 2024-07-15 | Delivery Management | Not Started
Closing | Post-Delivery Review & Documentation Finalization | 2024-07-16 | 2024-07-31 | Project Management Office (PMO) | Not Started
Last Updated: April 5, 2024 ¦ Prepared for Office Use