## Worksheet
Logistics Planning - Project Timeline
Task ID | Task Description | Start Date | End Date | Status | Responsible Party | Budget (USD)
T001 | Initial Planning & Requirements Gathering | 2025-04-01 | 2025-04-15 | In Progress | Logistics Team Lead | $8,500
T002 | Route Optimization & Transport Planning | 2025-04-16 | 2025-04-30 | Scheduled | Supply Chain Analysts | $15,750
T003 | Warehouse Inspection & Preparation | 2025-04-18 | 2025-05-10 | Scheduled | FACILITY Manager | $6,300
T004 | Carrier Contract Negotiation & Finalization | 2025-05-11 | 2025-05-25 | Scheduled | Purchasing Department | $18,900
T005 | Inventory Deployment & Loading Schedule | 2025-05-26 | 2025-06-14 | Scheduled | Operations Coordinator | $14,450
T006 | Real-Time Tracking System Integration | 2025-05-31 | 2025-06-18 | Scheduled | IT & Logistics Tech Team | $9,800
T007 | Final Delivery & Handover to Client | 2025-06-19 | 2025-06-30 | Scheduled | Project Manager | $7,250
Total Project Budget: | [5 empty] | $81,000