## Worksheet
Logistics Planning - Project Timeline (Planning View)
Task ID | Task Name | Planned Dates |  |  |  | Responsible Team | Status
|  | Start Date | End Date | Duration (days) | Milestone?
Phase 1: Planning & Coordination
PLN-001 | Define Logistics Requirements | 2025-04-01 | 2025-04-10 | 10 | Yes | Logistics Team | In Progress
Phase 2: Supplier & Carrier Selection
SEL-001 | Identify and Pre-Qualify Carriers | 2025-04-11 | 2025-04-25 | 15 | No | Procurement Team | Pending
Phase 3: Route & Schedule Optimization
RTE-001 | Map Optimal Delivery Routes | 2025-04-26 | 2025-05-15 | 21 | No | Distribution Team | In Progress
Phase 4: Implementation & Monitoring
IMP-001 | Execute First Shipment Batch | 2025-05-16 | 2025-06-30 | 46 | No | Operations Team | Pending
Phase 5: Review & Closure
REV-001 | Conduct Post-Implementation Review | 2025-07-01 | 2025-07-15 | 15 | No | All Stakeholders | Pending
Total Duration: | [5 empty] | 107 days
Legend:Milestone– Key event in the timeline.
Statuses: Pending ¦ In Progress ¦ Complete
This document is a planning view for logistics project timeline. Last updated on April 5, 2025.