## Worksheet
Logistics Planning - Project Timeline
Phase | Task Name | Start Date | End Date | Responsible Team/Person | Status
Planning & Coordination | Define project scope and deliverables | 2023-10-01 | 2023-10-05 | Project Manager | Pending
| Identify key logistics partners and suppliers | 2023-10-06 | 2023-10-15 | Procurement Team | In Progress
| Create detailed logistics schedule and routing plan | 2023-10-16 | 2023-10-25 | Logistics Coordinator | In Progress
Execution Phase (Oct 26 - Dec 31)
Transportation Setup | Finalize carrier contracts and freight agreements | 2023-10-26 | 2023-11-10 | Logistics Manager | In Progress
| Dispatch initial shipment batches to regional hubs | 2023-11-15 | 2023-12-05 | Fleet Operations Team | In Progress
Monitoring & Adjustment (Jan 1 - Mar 31)
Monitoring & Optimization | Track shipment performance and KPIs weekly | 2024-01-01 | 2024-03-31 | Operations Analyst | Pending
| Adjust routing and schedules based on real-time data | 2024-01-15 | 2024-03-31 | Supply Chain Team | Pending
Final Review & Closure (Apr 1 - Apr 15)
Closure Phase | Conduct post-project logistics review meeting | 2024-04-01 | 2024-04-10 | Project Manager, Logistics Lead | Pending
| Document lessons learned and update process manual | 2024-04-11 | 2024-04-15 | Process Improvement Team | Pending