## Worksheet
Logistics Planning - Project Timeline
Task ID | Task Description | Start Date | End Date | Status | Responsible Team
TASK-001 | Route Planning & Optimization | 2024-04-01 | 2024-04-15 | In Progress | Transportation Team
TASK-002 | Warehouse Inventory Audit | 2024-04-05 | 2024-04-18 | In Progress | Inventory Management
TASK-003 | Vendor Contract Finalization | 2024-04-10 | 2024-04-25 | Pending | Purchasing Department
TASK-004 | Equipment Maintenance Schedule | 2024-04-12 | 2024-05-15 | In Progress | Maintenance Team
TASK-005 | Delivery Capacity Assessment | 2024-04-18 | 2024-05-10 | Pending | Operations Planning
TASK-006 | Driver Training & Certification | 2024-05-01 | 2024-05-31 | Pending | HR & Safety Team
TASK-007 | Final Logistics Simulation Run | 2024-05-15 | 2024-06-15 | Pending | Project Management Office