## Worksheet
Logistics Planning - Project Timeline (Report Version)
Phase | Task | Start Date | End Date | Status | Responsible Team | Budget Allocation (USD)
Planning & Initiation | Requirement Gathering | 2024-04-01 | 2024-04-15 | In Progress | Logistics Team A | $15,000
Planning & Initiation | Resource Allocation Planning | 2024-04-16 | 2024-04-30 | Pending | Operations Management | $8,500
Execution Phase I | Supplier Onboarding & Contracts Signing | 2024-05-01 | 2024-05-15 | Pending | Sourcing & Procurement | $36,750
Execution Phase I | Warehouse Setup Preparation | 2024-05-16 | 2024-06-10 | Pending | Fleet & Facilities Team | $45,300
Execution Phase II | First Shipment Trial Run (Pilot) | 2024-06-11 | 2024-06-30 | Pending | Logistics Execution Unit | $58,900
Execution Phase II | Route Optimization & Monitoring Setup | 2024-07-01 | 2024-07-31 | Pending | Data Analytics Team | $39,650
Monitoring & Evaluation | Performance Review (Mid-Term) | 2024-08-15 | 2024-08-31 | Pending | Quality Assurance & Project Oversight | $17,500
Total Project Cost | [5 empty] | $281,600
Report Generated on:¦ Version 1.0 (Report Edition)