## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Responsible Team
T001 | Procure raw materials | 2024-04-01 | 2024-04-15 | In Progress | Supply Chain
T002 | Manufacturing Setup | 2024-04-16 | 2024-05-10 | Pending | Production Team
T003 | Quality Assurance Testing | 2024-05-11 | 2024-05-25 | Pending | QA Department
T004 | Packaging & Labeling | 2024-05-26 | 2024-06-15 | Pending | Logistics Team
T005 | Final Inspection & Approval | 2024-06-16 | 2024-06-25 | Pending | Quality Control
T006 | Shipping Coordination | 2024-06-26 | 2024-07-15 | Pending | Logistics Team
T007 | Distribution to Regional Warehouses | 2024-07-16 | 2024-08-15 | Pending | Transportation Team
Note: This timeline is subject to change based on supply chain updates and project milestones.