## Worksheet
Logistics Planning - Project Timeline Summary View
Phase | Activity | Timeline |  |  | Responsible Team | Status
|  | Start Date | End Date | Duration (Days)
Planning Phase | Requirements Gathering | 2024-04-01 | 2024-04-15 | 15 | Logistics Team | In Progress
| Route Optimization Analysis | 2024-04-16 | 2024-04-30 | 15 | Data Analytics Group | Pending
Execution Phase | Vendor Procurement & Contracts | 2024-05-01 | 2024-05-15 | 15 | Purchasing Department | In Progress
| Transportation Scheduling Setup | 2024-05-16 | 2024-05-31 | 16 | Operations Team | Pending
| Fleet Preparation & Maintenance Check | 2024-06-01 | 2024-06-15 | 15 | Maintenance Team | Pending
Total Duration (Planned) |  |  | 61 days
Note:This summary view provides an overview of key milestones and timelines for the logistics project planning. Status updates are reviewed weekly.