## Worksheet
Logistics Planning - Project Timeline (Team Use)
Task ID | Task Name | Responsible Team Member(s) | Start Date | End Date | Status | Notes / Dependencies
T001 | Finalize Logistics Strategy | Operations Team | 2024-04-01 | 2024-04-15 | In Progress | Prioritize regional distribution routes.
T002 | Vendor Contract Negotiations | Procurement Team | 2024-04-10 | 2024-05-15 | Pending | Requires approval from Legal.
T003 | Warehouse Capacity Assessment | Fleet & Storage Team | 2024-04-18 | 2024-05-10 | In Progress | Include seasonal inventory spikes.
T004 | Schedule Transport Routes & Vehicles | Logistics Coordinator | 2024-05-16 | 2024-06-30 | Pending | Coordinate with drivers and delivery windows.
T005 | Risk Assessment & Contingency Planning | Risk Management Team | 2024-06-15 | 2024-07-15 | Pending | Include weather, supply chain delays.
T006 | Team Training & Onboarding | HR & Ops Team | 2024-07-16 | 2024-07-31 | Pending | Ensure all staff are trained.
T007 | Final Timeline Review Meeting | Project Lead & Stakeholders | 2024-08-15 | 2024-08-15 | Pending | Approve final plan.
Total Tasks: |  | 7
Last updated: April 5, 2024 ¦ Designed for internal team use and collaboration.