## Worksheet
Logistics Planning - Project Timeline Template
Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person | Notes/Dependencies
Phase 1: Planning & Preparation
1.1 | Define project scope and logistics objectives | 2024-04-01 | 2024-04-05 | In Progress | Project Manager, Logistics Team | Review stakeholder requirements and deliverables.
1.2 | Identify key delivery locations and routes | 2024-04-06 | 2024-04-10 | Pending | Route Planning Specialist | Use GIS mapping tools for optimization.
Phase 2: Resource Allocation
2.1 | Allocate transportation assets (vehicles, vessels) | 2024-04-11 | 2024-04-15 | Pending | Fleet Manager | Confirm availability with vendors.
2.2 | Schedule warehouse and storage capacity | 2024-04-16 | 2024-04-18 | Pending | Warehouse Coordinator | Negotiate with third-party logistics providers.
Phase 3: Execution
3.1 | Initiate shipment dispatch from origin point | 2024-04-19 | 2024-05-15 | Pending | Logistics Coordinator | Track in real-time via GPS and logistics software.
3.2 | Maintain inventory and transit monitoring | 2024-04-19 | 2024-05-15 | Pending | Supply Chain Analysts | Daily status reports required.
Phase 4: Finalization
4.1 | Confirm delivery and receipt at destination points | 2024-05-16 | 2024-05-18 | Pending | Delivery Supervisor, Site Managers | Obtain signed delivery confirmations.
4.2 | Conduct post-project review and documentation | 2024-05-19 | 2024-05-21 | Pending | Project Manager, QA Team | Update logistics best practices and lessons learned.
Total Duration: |  |  | 2024-04-01 to 2024-05-21 | Template Version: 1.3 ¦ Last Updated: April 5, 2024