## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Assigned To | Status | Progress (%)
TL-001 | Route Planning & Approval | 2023-10-01 | 2023-10-15 | 15 | Jane Smith | In Progress | 75%
TL-002 | Fleet Maintenance & Inspection | 2023-10-16 | 2023-10-25 | 10 | Mike Johnson | Pending | 0%
TL-003 | Loading & Packaging Preparation | 2023-10-18 | 2023-10-30 | 13 | Sarah Lee | In Progress | 65%
TL-004 | Transport Execution (Phase 1) | 2023-10-31 | 2023-11-15 | 16 | Tom Brown | Pending | 0%
TL-005 | Delivery & Handover (Site A) | 2023-11-16 | 2023-11-30 | 15 | Lisa Wong | Pending | 0%
TL-006 | Final Documentation & Review | 2023-12-01 | 2023-12-15 | 15 | Daniel Park | Pending | 0%
Total Tasks: | [6 empty] | 6