## Worksheet
Week | Task | Responsible Party | Start Date | End Date | Status
Week 1 | Project Kickoff & Planning | Logistics Manager | 04/01/2024 | 04/05/2024 | In Progress
Week 2 | Route Optimization & Vendor Scheduling | Transport Coordinator | 04/08/2024 | 04/12/2024 | In Progress
Week 3 | Inventory Allocation & Warehouse Prep | Warehouse Supervisor | 04/15/2024 | 04/19/2024 | In Progress
Week 4 | Equipment Inspection & Dispatch Readiness | Fleet Manager | 04/22/2024 | 04/26/2024 | In Progress
Week 5 | First Shipment Dispatch & Tracking Setup | Logistics Coordinator | 04/29/2024 | 05/03/2024 | In Progress
Week 6 | Performance Review & Feedback Collection | Project Lead | 05/06/2024 | 05/10/2024 | In Progress
Week 7 | Final Adjustments & Closure Report Preparation | Logistics Manager | 05/13/2024 | 05/17/2024 | In Progress
Week 8 | Project Closure & Handover to Operations | Project Lead | 05/20/2024 | 05/24/2024 | In Progress