## Worksheet
Task ID | Task Name | Responsible Team | Start Date | End Date | Status | Priority
001 | Route Planning | Logistics Team | 2024-04-01 | 2024-04-15 | In Progress | High
002 | Vehicle Allocation | Fleet Management | 2024-04-10 | 2024-04-25 | To Do | High
003 | Driver Scheduling | HR & Operations | 2024-04-15 | 2024-04-30 | To Do | Medium
004 | Warehouse Preparation | Warehouse Team | 2024-04-05 | 2024-04-28 | In Progress | High
005 | Delivery Monitoring System Setup | Tech Team | 2024-04-20 | 2024-05-15 | To Do | Medium
Total Tasks: | [5 empty] | 5