## Worksheet
Logistics Planning - Project Tracker (Extended)
Project ID | Project Name | Start Date | End Date | Status | Assigned Team | Budget (USD) | Priority Level
Key Logistics Milestones & Deliverables
LP-2024-001 | North American Supply Chain Upgrade | Jan 5, 2024 | Jun 30, 2024 | In Progress | Supply Chain Team A | $1.8M | High
|  | Milestone 1:Warehouse Modernization Complete | Mar 15, 2024 | In Progress
|  | Milestone 2:New Distribution Routes Finalized | Apr 20, 2024 | In Progress
|  | Milestone 3:Vendor Contracts Signed | May 10, 2024 | Pending
LP-2024-005 | EU Regional Distribution Expansion | Feb 1, 2024 | Sep 30, 2024 | Completed | Logistics & Compliance Team B | $950K | Medium
|  | Milestone 1:Regulatory Approvals Obtained | Mar 30, 2024 | Completed
|  | Milestone 2:New Hub Opened (Berlin) | Jun 15, 2024 | Completed
|  | Milestone 3:First Full Month of Operations | Sep 1, 2024 | Completed
LP-2024-011 | Asia-Pacific Cold Chain Logistics Upgrade | Mar 15, 2024 | Dec 31, 2024 | Delayed (Pending Permits) | Cold Chain Specialized Team C | $3.2M | High
|  | Milestone 1:New Refrigerated Warehouses Built | Jun 30, 2024 | Delayed
|  | Milestone 2:Equipment Installation & Calibration | Sep 15, 2024 | Pending
|  | Milestone 3:Pilot Delivery Run (Singapore → Tokyo) | Nov 10, 2024 | Pending
LP-2024-018 | Digital Tracking System Integration | Jan 10, 2024 | Apr 30, 2024 | Completed | Tech & Data Team D | $580K | Medium
|  | Milestone 1:System Architecture Finalized | Feb 28, 2024 | Completed
|  | Milestone 2:Pilot Integration with 3 Warehouses | Mar 15, 2024 | Completed
|  | Milestone 3:Full System Rollout Completed | Apr 30, 2024 | Completed
Last Updated: April 5, 2024 ¦ This tracker supports logistics planning and project tracking for global supply chains.