## Worksheet
Monthly Project Tracker - Logistics Planning
Project ID | Project Name | Department | Planned Start Date | Planned End Date | Status | Budget (USD) | Actual Progress (%) | Risk Level
LP-2024-001 | Port Expansion Phase I | Maritime Logistics | Jan 5, 2024 | Apr 30, 2024 | In Progress | $1,850,000 | 68% | Medium
LP-2024-002 | Air Cargo Hub Optimization | Aviation Logistics | Feb 1, 2024 | Jun 30, 2024 | On Hold | $950,000 | 35% | High
LP-2024-003 | Regional Distribution Network Upgrade | Road & Rail Logistics | Jan 15, 2024 | Mar 31, 2024 | In Progress | $3,100,000 | 87% | Low
LP-2024-004 | Digital Freight Forwarding System | Technology Integration | Mar 1, 2024 | Jul 31, 2024 | Planning | $1,500,000 | 15% | Medium
LP-2024-005 | Seasonal Inventory Buffering Strategy | Supply Chain Planning | Jan 1, 2024 | Dec 31, 2024 | Completed | $750,000 | 100% | N/A