## Worksheet
Logistics Planning - Advanced Schedule Planner
Optimize shipments, track timelines, and manage resources efficiently
Task ID | Activity Description | Assigned To | Start Date | End Date | Status | Priority | Scheduled Route (Origin → Destination)
#LGP-001 | Procure raw materials | John Doe (Supply Chain) | 2025-04-01 | 2025-04-15 | Pending | High | Seattle → Houston (Transit: 7 days)
#LGP-002 | Dispatch warehouse loading | Alice Smith (Operations) | 2025-04-16 | 2025-04-18 | In Progress | Medium | Houston → Atlanta (Transit: 3 days)
#LGP-003 | Finalize delivery scheduling | Robert Lee (Logistics) | 2025-04-19 | 2025-04-21 | In Progress | High | Atlanta → Chicago (Transit: 4 days)
#LGP-004 | Delivery confirmation & documentation | Sarah Wilson (Customer Service) | 2025-04-22 | 2025-04-23 | Pending | Medium | Chicago → Denver (Transit: 5 days)
#LGP-005 | Post-delivery review & feedback collection | Liam Brown (Quality) | 2025-04-24 | 2025-04-30 | Pending | Low | Denver → Phoenix (Transit: 6 days)
© 2025 Logistics Planning System ¦ Advanced Schedule Planner v3.1 ¦ Data updated on April 4, 2025