## Worksheet
Logistics Planning - Schedule Planner - Analysis View
Task ID | Activity Description | Planned Schedule |  |  |  | Actual Performance |  |  | Status
|  | Start Date | End Date | Duration (Days) | Owner | Actual Start | Actual End | Delay (Days)
LP-001 | Pickup Preparation | 2024-06-15 | 2024-06-17 | 3 | J. Smith | 2024-06-15 | 2024-06-18 | 1 | Pending Review
LP-002 | Transportation Booking | 2024-06-18 | 2024-06-19 | 2 | M. Lee | 2024-06-18 | 2024-06-19 | 0 | In Progress
LP-003 | Customs Clearance Preparation | 2024-06-20 | 2024-06-21 | 2 | R. Patel | - | - | - | Pending Start
LP-004 | Final Delivery Confirmation | 2024-06-25 | 2024-06-27 | 3 | J. Brown | - | - | -
Delivery Milestones Summary (All Locations)
Total Tasks: |  | 4 |  | 10 days |  |  |  | Total Delays: | +1 days