## Worksheet
Logistics Planning Schedule Planner (Extended Version)
Task ID | Activity Name | Department | Schedule Dates |  |  | Resource Allocation |  |  |  | Priority Level | Status
|  |  | Start Date | Due Date | Duration (Days) | Personnel Assigned | Vehicles/Equipment | Budget Allocated ($)
LOG-001 | Raw Material Procurement | Purchasing | 2025-04-01 | 2025-04-15 | 15 | Jane Doe, Mike Lee | Lorries - 3, Forklifts - 2 | 48,000 | High | On Time
LOG-002 | Warehouse Receiving & Inspection | Operations | 2025-04-16 | 2025-04-18 | 3 | Alice Smith, Carlos Rivera | Cargo Trolleys - 5, Scanners - 3 | 7,500 | High | On Time
LOG-003 | Inventory Sorting & Labeling | Warehouse Team | 2025-04-19 | 2025-04-21 | 3 | Tina Chen, Omar Khan, Sam Reed | Label Printers - 4, RFID Tags - 1k units | 6,200 | High | On Time
LOG-004 | Prep for Distribution (Packaging) | Packaging Unit | 2025-04-22 | 2025-04-26 | 5 | Lisa Wong, David Patel, Emma Taylor | Packing Machines - 3, Boxes - 10k units | 18,400 | High | On Time
LOG-005 | Dispatch Coordination (Regional) | Transportation Mgmt | 2025-04-27 | 2025-04-30 | 4 | Ryan Foster, Nia Johnson, Tomás Ruiz | Trucks - 8, GPS Trackers - 8 units | 64,500 | High | On Time
LOG-006 | Delivery to North Region (Phase 1) | Field Logistics | 2025-05-01 | 2025-05-14 | 14 | Daniel Park, Grace Liu, Ben Miller, Olivia Green | Lorries - 6 (with refrigeration), Trailers - 3 | 98,200 | Critical | On Time
LOG-007 | Delivery to South Region (Phase 1) | Field Logistics | 2025-05-01 | 2025-05-14 | 14 | Maria Silva, James Clark, Zoe Nguyen, Leo Hall | Lorries - 6 (standard), Trailers - 3 | 89,000 | Critical | On Time
LOG-008 | Delivery to East Region (Phase 1) | Field Logistics | 2025-05-01 | 2025-05-14 | 14 | Alex Turner, Chloe Kim, Raj Desai, Neil White | Lorries - 6 (standard), Trailers - 3 | 92,700 | Critical | On Time
LOG-009 | Delivery to West Region (Phase 1) | Field Logistics | 2025-05-01 | 2025-05-14 | 14 | Sophie Reed, Ian Stewart, Fatima Ahmed, Luca Rossi | Lorries - 6 (standard), Trailers - 3 | 90,500 | Critical | On Time
LOG-010 | Post-Delivery Reporting & Feedback Loop | Analytics & QA | 2025-05-15 | 2025-05-17 | 3 | Elena Martinez, Brian O'Connor, Priya Kapoor, Mark Wu | Data Dashboard Tools, Survey Software | 8,600 | Medium | On Time
Total Project Summary |  |  |  | 106 Days (Cumulative) |  |  | Total Resources: | $785,600 | Final Status: On Schedule & Executing