## Worksheet
Logistics Planning - Schedule Planner (Manager View)
Task ID | Task Description | Assigned To | Department | Scheduled Start Date | Scheduled End Date | Status
Project: Logistics Coordination Q3 2024 |  | Planner: Jane Smith ¦ Last Updated: May 17, 2024 |  |  | Progress %
Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Overall Timeline (Weeks)
TASK-001 | Route Optimization Analysis | Mark Johnson | Transportation | 2024-05-20 | 2024-05-23 | In Progress (67%)
TASK-002 | Warehouse Inventory Audit | Lisa Chen | Inventory Management | 2024-05-18 | 2024-05-21 | Pending (0%)
TASK-003 | Carrier Contract Review | Robert King | Procurement | 2024-05-19 | 2024-05-25 | Completed (100%)
TASK-004 | Delivery Schedule Finalization | Sarah Patel | Logistics Operations | 2024-05-22 | 2024-05-31 | In Progress (45%)
TASK-005 | Driver Training Sessions (Q3) | James Wilson | HR & Operations | 2024-05-24 | 2024-06-15 | Pending (0%)
Total Tasks: | [5 empty] | 5
Completed: | [5 empty] | 1 (20%)
In Progress: | [5 empty] | 2 (40%)
Pending: | [5 empty] | 2 (40%)