## Worksheet
Logistics Planning - Schedule Planner (Planning View)
Task ID | Activity Description | Start Date | End Date | Status | Resource Assigned | Priority
Pre-shipment Activities
PRC001 | Order Processing & Verification | 2025-04-01 | 2025-04-03 | In Progress | John Doe (Logistics) | High
PRC002 | Packing & Labeling Preparation | 2025-04-04 | 2025-04-06 | Not Started | Alice Smith (Warehouse) | High
Shipment Execution
SHM001 | Loading & Securing Cargo | 2025-04-07 | 2025-04-10 | Not Started | Mike Johnson (Fleet) | High
Transit & Tracking
TRN001 | In-Transit Monitoring (Domestic) | 2025-04-11 | 2025-04-18 | Not Started | Laura Brown (Tracking) | Medium
Delivery & Finalization
DLY001 | On-Delivery Inspection & Documentation | 2025-04-19 | 2025-04-19 | Not Started | Tony Wilson (Delivery) | High
Total Planned Tasks: |  |  | 6
Legend:
●Header Row - Planning Overview
Section Header- Activity Grouping
● High Priority
● Medium Priority
Generated on:¦ Logistics Planning - Schedule Planner (Planning View)