## Worksheet
Task | Department | Start Date | End Date | Status | Assigned To | Budget (USD)
Pickup Goods from Warehouse A | Transportation | 2024-10-01 | 2024-10-03 | In Progress | Jane Smith | $8,500.00
Customs Clearance - Port B | Compliance & Customs | 2024-10-04 | 2024-10-06 | Pending | Mike Johnson | $3,750.00
Transit to Distribution Center C | Transportation | 2024-10-07 | 2024-10-10 | Scheduled | Lisa Brown | $15,600.00
Final Delivery to Retail Store D | Delivery Operations | 2024-10-11 | 2024-10-13 | Scheduled | Daniel Lee | $5,300.00
Total Estimated Logistics Cost: | [5 empty] | $33,150.00