## Worksheet
Logistics Planning - Team Use Schedule Planner
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Notes / Remarks (Optional)
LP-001 | Procure shipping containers for Q3 delivery | Sarah Johnson | 2025-04-05 | 2025-04-18 | In Progress | Supplier quote pending approval.
LP-002 | Coordinate with warehouse for inbound loading schedule | Mark Rodriguez | 2025-04-06 | 2025-04-15 | Pending | Waiting on warehouse availability confirmation.
LP-003 | Finalize route planning for regional distribution hubs | Aisha Patel | 2025-04-10 | 2025-04-28 | In Progress | Map updated after new highway closures.
LP-004 | Conduct team briefing on revised logistics timeline | James Carter | 2025-04-16 | 2025-04-16 | Completed | Meeting held successfully with all key stakeholders.
LP-005 | Update tracking system with real-time shipment data | Lena Wu | 2025-04-18 | 2025-04-30 | Pending | Integration testing in progress.
LP-006 | Review and validate final delivery schedule with client | Thomas Bennett | 2025-04-21 | 2025-04-30 | In Progress | Awaiting client feedback on proposed dates.
LP-007 | Prepare contingency plan for weather disruptions | Elena Martinez | 2025-04-14 | 2025-04-31 | Pending | Draft to be reviewed by risk management team.
LP-008 | Final audit of logistics documentation and compliance | David Kim | 2025-04-25 | 2025-04-31 | In Progress | Checking all shipment records against policy.
LP-009 | Send delivery confirmation to all regional teams | Sophie Dubois | 2025-04-31 | 2025-04-31 | Pending | Final checks pending prior to distribution.
LP-010 | Conduct post-mortem meeting for Q2 logistics operations | Ryan O'Connor | 2025-05-05 | 2025-05-10 | Pending | Date scheduled after Q3 planning completes.
This schedule is managed by the Logistics Planning Team. All updates to task status and notes should be made in real time.