## Worksheet
Logistics Planning - Schedule Planner
Template Version | V2.1 - Logistics & Supply Chain Optimization
Schedule Overview
Project ID | Delivery Date | Origin Location | Destination Location | Carrier Name | Shipping Method |  | Estimated Transit Time (Days)
LOG-001 | 2024-11-30 | Chicago, IL - Distribution Center | Boston, MA - Retail Hub | FedEx Logistics Inc. | Ground Express (Priority) |  | 3 days | 1.5 days (Express Add-on)
LOG-002 | 2024-12-05 | Dallas, TX - Warehousing Zone A | Denver, CO - Distribution Hub West | TNT Freight Co. | Full Truckload (FTL) |  | 4 days | -
Delivery Schedule Details
Scheduled Event | Date & Time (UTC) | Activity Type | Route Segment | Vehicle ID/Tracking # | Status | Pickup Location | Delivery Location | Dock/Gate No.
Container Loading (Origin) | 2024-11-25 08:30:00 | Loading / Preparation | Chicago → Indianapolis | CAR-LG876543 | In Progress | Chicago DC - Bay 12A | Indianapolis Depot - Dock 4B | B-5
Transit (Mid-Route) | 2024-11-26 14:00:00 | En Route Monitoring | Indianapolis → Cincinnati | CAR-LG876543 | On Time | Cincinnati Terminal - Yard 3A | N/A (En Route)
Final Delivery Drop-Off (Destination) | 2024-11-28 09:00:00 | Delivery & Unloading | Cincinnati → Boston (via Hub) | CAR-LG876543 | Scheduled | Boston Hub - Gate C2 | Final Customer Site - Bay 10D
Notes & Adjustments (For Planner Use)
Critical Notes |  |  |  | Revised ETA Due to Weather (Route Change) | Winter storm forecast in Mid-Atlantic region; rerouting via Pittsburgh instead of Cleveland. Additional 1-day delay expected.
Planner Comments |  |  |  | Next Review Date | 2024-11-23 08:00:00 (Daily Logistics Sync)