## Worksheet
Logistics Planning - Schedule Planner (Tracking View)
Task ID | Activity Description | Assigned To | Start Date | Due Date | Status | % Complete
LP-001 | Procurement of Materials | John Smith | 2024-04-05 | 2024-04-15 | In Progress | 75%
LP-002 | Vehicle Scheduling & Route Planning | Sarah Johnson | 2024-04-06 | 2024-04-18 | In Progress | 65%
LP-003 | Warehouse Loading Preparation | Mike Brown | 2024-04-10 | 2024-04-16 | Pending | 5%
LP-004 | Transportation Dispatch & Tracking | Lisa Wong | 2024-04-15 | 2024-04-30 | Pending | 0%
LP-005 | Delivery Confirmation & Documentation | Daniel Lee | 2024-04-28 | 2024-05-15 | Pending | 0%
Overall Progress:68%
Last Updated: April 5, 2024