## Worksheet
Logistics Planning - Task Manager (Analysis View)
Task ID | Task Description | Assigned To | Priority | Status | Planned Start Date | Planned End Date | Budget (USD) | Actual Cost (USD)
TASK-001 | Procure raw materials for Q3 shipment | Jane Doe | High | In Progress | 2024-07-01 | 2024-07-15 | $58,350.00 | $56,983.42
TASK-002 | Arrange transportation for regional distribution hubs | John Smith | Medium | Not Started | 2024-07-10 | 2024-07-31 | $89,500.00 | $-
TASK-003 | Optimize warehouse layout for inventory turnover | Alice Brown | High | Completed | 2024-06-15 | 2024-06-30 | $15,789.35 | $14,978.61
TASK-004 | Coordinate customs clearance for international shipments | Robert Lee | High | Delayed | 2024-07-05 | 2024-07-18 | $34,650.00 | $36,123.89
TASK-005 | Conduct supplier performance review cycle | Sophia Clark | Medium | In Progress | 2024-07-12 | 2024-07-31 | $8,950.00 | $6,345.78
Total Tasks:5 ¦Completed:1 ¦In Progress:2 ¦Not Started:1 ¦Delayed:1
Budget Forecast: $207,239.35 ¦ Actual Spend: $114,432.68 (55% of forecast)