## Worksheet
Task ID | Task Name | Department | Assignee | Start Date | End Date | Priority | Status | Progress (%)
T-001 | Finalize Delivery Route Planning | Logistics | Sarah Johnson | 2024-05-01 | 2024-05-15 | High | In Progress | 65%
T-002 | Procure Refrigerated Trucks | Fleet Management | James Reed | 2024-05-03 | 2024-05-25 | Critical | Pending | 20%
T-003 | Update Warehouse Inventory System | Supply Chain | Lisa Chen | 2024-05-05 | 2024-06-15 | Medium | Not Started | 0%
T-004 | Schedule Cross-Docking Operations | Logistics Coordination | Michael Torres | 2024-05-08 | 2024-05-31 | High | In Progress | 80%
T-005 | Conduct Driver Safety Training | HR & Operations | Emily Watson | 2024-05-10 | 2024-05-28 | Medium | In Progress | 45%
T-006 | Review Carrier Performance Metrics | Vendor Management | David Kim | 2024-05-15 | 2024-06-30 | Low | Not Started | 0%