## Worksheet
Logistics Planning - Time Tracker (Analysis View)
Task ID | Activity | Planned Start | Planned End | Actual Start | Actual End | Status | % Complete | Duration (Days) | Scheduled Hours | Actual Hours | Variance (Hrs)
T001 | Route Optimization | 2025-04-01 | 2025-04-05 | 2025-04-01 | 2025-04-06 | In Progress | 95% | 6.3 | 48 | 52.7 | 4.7
T002 | Warehouse Inventory Audit | 2025-04-03 | 2025-04-10 | 2025-04-03 | 2025-04-11 | Delayed | 88% | 7.6 | 64 | 73.5 |  | 9.5
Summary Metrics (Overall Progress)
Total Planned Tasks: |  |  |  | 18 |  | On-Time Completion: |  |  |  | 65%
Total Scheduled Hours: |  |  |  | 912 |  | Total Actual Hours: |  |  |  | 1,053.8
Critical Path Items (High Priority)
CPI-01 | Supplier Delivery Coordination | 2025-04-05 | 2025-04-13 | 2025-04-18 | N/A (Pending) | Blocked | -